## Summary
MyFinance Accounting Portal — Cost Summary
AI-assisted build (Claude Code) · figures in EUR · v1 · 31 May 2026
Development (one-time)
PoC — de-risk extraction & reconciliation | 1320
MVP — full multi-tenant product (labour) | 6480
Claude Code subscription (PoC+MVP build) | 135.1039
TOTAL development (PoC + MVP) | 7935.1039
Future phase (optional, rough) | 8464.1109
Running (recurring)
Expected — per month | 199
Expected — per year | 2388
Range — per month (low / high) | 93.5 | 427
Key assumptions
• Oversight rate €40/h; 1× Claude Code Max ≈ €180/mo; ~30 oversight hrs/week.
• Hours are HUMAN OVERSIGHT of Claude Code (code, tests, docs, user stories, IaC) — not full hand-coding.
• Running cost at MVP scale (~1–3k companies); OCR/LLM are the main variables.
• Stack: Java/Spring + worker on Hetzner, Supabase (DB+Auth+Storage), React PWA on Vercel/Cloudflare.
• Excludes VAT, third-party setup fees, and human end-user support. Editable inputs are blue.

## Assumptions
MyFinance Accounting Portal — Estimation Assumptions & Methodology
Development cost drivers
Oversight / review rate (€ per hour) | 40 | Your time guiding & reviewing Claude Code (blue = editable input)
Claude Code Max subscription (€ per month) | 90 | 1 seat, Max 5x tier
Oversight hours per week | 30 | Productive human hours/week during the build
Weeks per month | 4.33 | Constant
Running cost drivers (OCR)
Active client companies (MVP) | 1500 | Mid of ~1–3k target
Paid-OCR pages per company per month | 6 | Most uploads are text PDFs parsed free in-process; only photo/scanned receipts hit paid OCR
OCR price per 1,000 pages (€) | 7 | Managed Document-AI, pay-per-use
OCR monthly (expected, €) | 63
Methodology
• Development is performed by Claude Code, which writes the code, tests, documentation, user stories,
and infrastructure-as-code (Terraform). The hours below are HUMAN OVERSIGHT hours (guiding, reviewing,
correcting, integrating) — not full hand-coding effort. A traditional human-team build of this scope would
be several times higher in effort and cost.
• Development cost = oversight hours × rate + Claude Code subscription over the build duration.
• Build duration is derived from total hours ÷ (oversight hours/week × weeks/month).
• Running cost is a separate monthly estimate at MVP scale, shown low / expected / high.
• OCR and LLM usage are the main variable running costs; receipts-only OCR keeps it bounded, and a future
e-Factura/ANAF integration would remove most invoice processing entirely.
• Figures exclude VAT, one-off third-party setup (e.g. WhatsApp onboarding), and human end-user support.
• Hosting per architecture v1: Java/Spring + worker on Hetzner (always-on), Supabase (DB+Auth+Storage),
React PWA on Vercel/Cloudflare, managed Document-AI for receipts.

## Development
Development Estimation (AI-assisted build by Claude Code)
ID | Module / Workstream | Phase | Complexity | Oversight hrs | Labour cost
— PoC: de-risk extraction + reconciliation —
PoC-A | Scaffolding + minimal auth/company setup | PoC | Medium | 6 | 240
PoC-B | Extraction spike (VALIDATED on real BRD/BT/balance/D212 — build parser library) | PoC | High | 12 | 480
PoC-C | Reconciliation engine + missing-document detection (logic proven) | PoC | Med-High | 10 | 400
PoC-D | State-payment email auto-fill (amounts + deadline + treasury) | PoC | Medium | 5 | 200
| PoC subtotal |  |  | 33 | 1320
— MVP: full multi-tenant product —
MOD-01 | Tenant Administration | MVP | Medium | 6 | 240
MOD-02 | Users, Accounts & Access (Supabase Auth, RBAC, RLS) | MVP | Med-High | 8 | 320
MOD-03 | Client Company Management (tax profile, treasury, HR registry) | MVP | High | 8 | 320
MOD-04 | Document Intake & Reconciliation (core differentiator; logic proven) | MVP | High | 14 | 560
MOD-05 | Document Extraction Engine (per-bank parsers + per-decl XML mappers) | MVP | High | 13 | 520
MOD-06 | Financial Statements & Reports | MVP | Med-High | 8 | 320
MOD-07 | Fiscal Declarations & State Payments | MVP | Med-High | 7 | 280
MOD-08 | Payroll (State de plata) | MVP | Low-Med | 5 | 200
MOD-09 | Notifications Engine (email + in-app) | MVP | Med-High | 8 | 320
MOD-10 | Internal Tasks | MVP | Low | 4 | 160
MOD-11 | Dashboards (overview + tiles + new-companies; prototype-defined) | MVP | Medium | 8 | 320
MOD-12 | Audit, Security & GDPR | MVP | Medium | 8 | 320
MOD-13 | AI Chatbot + Knowledge Base (incl. guardrails spike) | MVP | High | 18 | 720
MOD-14 | Mobile / PWA (responsive, camera, web push) | MVP | Medium | 8 | 320
X-01 | Project setup, scaffolding & IaC (Terraform, Hetzner, Supabase, CI/CD) | MVP | High | 12 | 480
X-02 | Integration & end-to-end testing / hardening | MVP | High | 14 | 560
X-03 | Deployment, environments & observability | MVP | Medium | 8 | 320
X-04 | Bilingual i18n (Romanian + English) | MVP | Low | 2 | 80
X-05 | Documentation + user-story backlog (Claude-generated, you review) | MVP | Low | 3 | 120
| MVP subtotal |  |  | 162 | 6480
— Future (rough, optional) —
F-01 | WhatsApp notification channel | Future | Low-Med | 12 | 480
F-02 | e-Factura / ANAF SPV integration | Future | High | 30 | 1200
F-03 | In-app two-way messaging | Future | Medium | 24 | 960
F-04 | Native mobile app | Future | Very High | 60 | 2400
F-05 | Per-employee payslip distribution | Future | Low-Med | 12 | 480
F-06 | Payroll-system integration | Future | Medium | 20 | 800
F-07 | Per-tenant template customization | Future | Medium | 16 | 640
F-08 | Per-employee company-access restriction | Future | Low | 10 | 400
F-09 | Database-per-tenant premium tier | Future | Med-High | 24 | 960
| Future subtotal |  |  | 208 | 8320
Cost summary
| PoC — labour (oversight) |  |  |  | 1320
| MVP — labour (oversight) |  |  |  | 6480
| PoC+MVP — total oversight hours |  |  |  | 195
| PoC+MVP — build duration (months) |  |  |  | 1.5012
| PoC+MVP — Claude Code subscription |  |  |  | 135.1039
| PoC+MVP — TOTAL development cost |  |  |  | 7935.1039
| Future — labour (oversight) |  |  |  | 8320
| Future — build duration (months) |  |  |  | 1.6012
| Future — Claude Code subscription |  |  |  | 144.1109
| Future — TOTAL development cost |  |  |  | 8464.1109

## Running Cost
Running Cost — Monthly (MVP scale)
Item | Notes | Low (€/mo) | Expected (€/mo) | High (€/mo)
Hetzner — backend app server | Spring API (CPX31-class) | 9 | 15 | 30
Hetzner — worker server | Extraction/notification worker (CPX21-class) | 5 | 8 | 16
Redis / queue | Small instance or Postgres pgmq | 0 | 5 | 10
Supabase Pro | Postgres + Auth + Storage (+ storage overage) | 23 | 28 | 45
Frontend hosting | Vercel/Cloudflare (free → Pro) | 0 | 0 | 20
Document-AI OCR | Receipts only, pay-per-use (=Assumptions OCR) | 31.5 | 63 | 126
LLM (chatbot) | Usage-based, modest at MVP | 20 | 50 | 120
Transactional email | Report/tax/payroll/notification email | 0 | 20 | 40
Domain, TLS, misc | DNS, certs, monitoring buffer | 5 | 10 | 20
Total per month |  | 93.5 | 199 | 427
Total per year |  | 1122 | 2388 | 5124
OCR and LLM are the main variable costs; receipts-only OCR bounds them, and a future e-Factura integration removes most invoice processing.